PRODUCT REQUIREMENT - PRD New York Sun Works Partner School Success Dashboard

| Prepared for | Megan & Amanda, New York Sun Works · Nishy, Shabiha, NYSW Executive Director & Directors |
| --- | --- |
| Prepared by | Pedro A. Martins, PMP · Pursuit × Mizuho Bank Nonprofit Builder Program |
| PRD approval / kickoff | Week of September 1, 2026 |
| Midpoint checkpoint | Week of September 29, 2026 |
| Demo Day | Wednesday, October 28, 2026 · Mizuho's offices |

This PRD reflects our PRD Workshop scoping session (Aug 26) and follow-up meetings with Megan and Amanda (Sept 2 and Sept 4). It defines what we are building, why it matters to NY Sun Works, and how we will deliver it within the six-week Pursuit × Mizuho Builder Program window.

1 · Problem & Goals

NY Sun Works builds hydroponic farms inside public school science classrooms across NYC — currently 370 schools, expanding to 400+ — and delivers a full PreK-12 climate and STEM curriculum. Its teams have no in-house technologist and no centralized way to see how each partner school is actually doing throughout the school year, because school data lives across Accelo (CRM), an annual teacher survey, Google Drive, and various Google Sheets that must be manually reviewed.

This results in struggling schools going unnoticed until it's time to report to funders — too late in the year to help a school recover. Gaps in data that should have been captured consistently throughout the year surface only at reporting time, and the manual review process itself consumes significant time for a small team.

| Goal | Description |
| --- | --- |
| Identify at-risk schools early | Flag schools whose engagement, support, or classroom health is slipping while there is still time to intervene. |
| Centralize school performance data | Replace manual cross-referencing of Accelo, surveys, and Sheets with one school-level Grade. |
| Support targeted staff intervention | Enable GST and program staff to prioritize outreach and support visits by need, not by guesswork. |
| Strengthen funder & partner reporting | Walk into funder reporting season, and funder/corporate visits, with complete, current, presentable data. |

2 · Who It's For

| User | Priority | Role and use of the tool |
| --- | --- | --- |
| GST / Maintenance Team (Operations Manager) | Primary | Sees an up-to-date Grade for partner schools in one place instead of checking multiple platforms, so they can step in to support schools and their team. |
| Development Team (Development Director) | Secondary | Knows as early as possible when a school's data is incomplete or performance is slipping, before it's too late to fix ahead of funder reporting. |
| Executive Leadership (Executive Director) | Tertiary | Uses a simple, consistent view of which schools are thriving vs. struggling to decide where to focus limited staff time and resources. |

3 · Out of Scope

- Development-team workflow integration across Monday.com, Gmail, and Slack (Track 2) — assessed as too broad and complex for the six-week window.

- Automated capture of external communications (e.g., elected-official emails) into any project-management tool.

- Raw, unprocessed data browsing across every source system (SurveyMonkey exports, Google Sheets) as a dashboard feature.

- A fourth grading component — Student Engagement, sourced from teacher surveys — deferred to a future version.

- Ingestion of the Accelo School Communication Stream until NYSW defines its export format.

4 · Data Sources

All Accelo assets export as Excel; the School Communication Stream format is still to be determined by NYSW.

| Source | Cadence / Format | Signal |
| --- | --- | --- |
| Accelo — GST Weekly Support Report | Weekly / Per visit · Asset/Excel | Visit frequency, systems running, seedlings, harvest, pests — feeds Teacher Engagement & Classroom/GST |
| Accelo — HC Performance Asset | Bi-annual (Fall/Spring) · Asset/Excel | Teacher relationship, admin/custodian involvement, classroom usability rubrics — feeds all three components |
| Accelo — Ed Team Curriculum Training & PD | Per session · Asset/Excel | Training completion, teacher rubric scores — feeds Teacher Engagement |
| Accelo — Events | Per session · Asset/Excel | Principal/teacher/student involvement at events — feeds Administration Support |
| Accelo — School Communication Stream | Ongoing, no fixed cadence · Format TBD | Auto-logged admin communication frequency — feeds Administration Support |
| SurveyMonkey — Teacher Survey | Annual · Excel | Teacher-reported engagement and classroom experience |
| Google Drive — Draft Maintenance Plan | Daily · Google Sheet | Proposal acceptances — feeds Administration Support |
| Google Drive — GST Photos | Weekly / Per visit · JPGs | Visual classroom status for the Snapshot view |
| Google Drive — School Profiles | Annual (start of SY) · Google Slides | Baseline school overview for the Profile view |
| Google Drive — Story Bank | Ongoing, no fixed cadence · Google Sheet | Qualitative quotes — feeds AI-generated note summaries |
| Email / Box — Thank You & Support Letters | Bi-annual (Fall/Spring) · Emails/PDFs | Qualitative signal of admin/funder relationship strength |

5 · What We're Building

One dashboard, three views per school. The MVP is a single core function: given a partner school, return its current Grade, the top drivers behind it, and whether it needs attention.

| Feature | Description |
| --- | --- |
| 1 · School Grade | Every school receives an overall Grade (letter grade or traffic-light tier — format confirmed Week 1), built from Teacher Engagement, Administration Support, and Classroom Maintenance/GST. |
| 2 · Grade Trend | How a school's overall Grade and each component have changed over the school year, so a slipping trend is visible before it becomes a crisis. |
| 3 · School Profile | Stable overview: assigned GST member, teacher/admin relationship history, training history, notes. |
| 4 · School Snapshot | Point-in-time classroom status as of the latest visit: systems running, seedlings, harvest, pest issues, photos — useful for identifying visit-ready schools. |
| 5 · At-Risk Alerts | Schools whose Grade drops below the healthy threshold are automatically flagged so staff can intervene mid-year rather than at reporting time. |
| 6 · Search, Filter & AI Summary | Search/filter the school list by borough or area manager; read an AI-generated summary of qualitative notes instead of every raw visit note. |

6 · User Journey

Primary journey — checking on a school

- User opens the school list, searchable and filterable by borough and area manager (GST member).

- User selects a school and sees its Grade view: overall Grade, the three component scores, and trend over the school year.

- User reviews the Snapshot for current classroom status as of the most recent visit.

- User drills into any component score to see the underlying visit/session records behind it.

- User reads an AI-generated summary of qualitative notes instead of reading every raw note.

- If the Grade has dropped below the healthy threshold, the user sees a flag prompting outreach or a support visit.

Secondary journey — preparing for a funder or corporate visit

- Development team member filters the school list for high-performing, visit-ready schools.

- User opens the Snapshot to confirm current classroom presentability and plant/harvest status.

- User checks the Profile to confirm admin relationship strength before booking the visit.

7 · Grading Framework

The Grade is built from three components, each fed by specific fields extracted from Accelo assets and the teacher survey. A fourth component — Student Engagement — was identified as a candidate for a future version.

| Component | Primary Inputs |
| --- | --- |
| Teacher Engagement | Training completion & attendance, teacher relationship/engagement rubric ratings, curriculum training rubric scores, teacher survey responses. |
| Administration Support | Custodian involvement, admin communication/engagement, funding/continuation concerns, visit scheduling flexibility, proposal acceptance timing. |
| Classroom Maintenance / GST | Visit frequency as a % of required cadence (not raw count, since cadence varies by school), systems running, harvest activity, pest issues, usability ratings. |

Key message: grading thresholds are not yet finalized. NY Sun Works (Megan, Amanda, Shabiha) will build two model school profiles — one high-performing, one low-performing — to anchor and validate the grading rubric before it is coded into the dashboard.

8 · Success Metrics

| Metric | Target |
| --- | --- |
| Time-to-identify a struggling school (North Star) | Flagged within the same reporting cycle it occurs — not discovered at funder-reporting time. |
| Coverage | 100% of active partner schools display a current Grade and Snapshot sourced from real NYSW data by Demo Day. |
| Speed of lookup | Staff can retrieve a school's status and supporting data in under a minute, vs. the current multi-platform manual review. |
| Grading validation | At least one below-threshold school correctly flagged against NYSW's own model-school validation during UAT. |
| Usability bar | NYSW confirms the dashboard is easier to use for a school check-in than their current process. |
| Handoff readiness | Clear, documented owner and maintenance plan on the NYSW side as of handoff (Oct 27). |

9 · Acceptance Criteria

What "done" means for each MVP requirement, to be validated during client-assisted UAT (Oct 13–24).

- Selecting any partner school returns an overall Grade and all three component scores within a few seconds, with no manual refresh step.

- Each component score displays the specific Accelo/survey records used to calculate it, so a score can be traced back to source data.

- A trend view shows at least two prior data points (or all available history) for each school's overall Grade and components.

- The Snapshot reflects the most recent visit's data and clearly shows the as-of date.

- Schools below the agreed healthy threshold appear in a distinct flagged/at-risk view, visible without opening each school individually.

- The school list can be filtered by borough and by area manager, and search returns the correct school by name.

- The AI-generated note summary reflects actual qualitative content on file and does not fabricate details.

- The dashboard runs on real NYSW data for at least one full end-to-end school record by the Week 3 architecture checkpoint.

- NYSW (Megan/Amanda) has signed off on data validation and grading output for a representative sample of schools before Demo Day.

10 · Timeline & Milestones

| Date | Milestone |
| --- | --- |
| Aug 26 | PRD Workshop — scoping session with NYSW |
| Week of Sept 1 | PRD finalized by NYSW, approved, kickoff |
| Week of Sept 8 | Start building: repo up, first end-to-end slice |
| Week of Sept 15 | Architecture up: main workflow callable on real data |
| Week of Sept 29 | Midpoint: build on track, presentation draft started |
| Week of Oct 6 | Feature-complete: everything in the revised PRD working |
| Oct 13–24 | Test, polish, stabilize: client-assisted UAT, handoff doc, rehearsals |
| Oct 28 | Demo Day at Mizuho: co-present the working product with NYSW |

Weekly deliverables — what "done" looks like

| Period | Deliverable |
| --- | --- |
| Week 1 · Sept 1–5 | Revised PRD in NYSW's own words approved by Stef; data inventory; stack/hosting/cost decisions; privacy check; access request statuses; meeting cadence confirmed. |
| Week 2 · Sept 8–12 | Repo up, environment working, first end-to-end slice in progress, real NYSW data in the build, first written client update sent (cc Stef). |
| Week 3 · Sept 15–19 | Core architecture in place, real data flowing through the full pipeline, data-findings note sent to NYSW, scope check against this PRD. |
| Midpoint · Sept 29 | Demo script first pass + slide outline shared with Stef; narrative anchored in NYSW's real numbers. |
| Week of Oct 6 | Feature-complete: every scoped feature working end-to-end on real data; testing plan for the final stretch. |
| Oct 13–24 | Client-assisted UAT, data validation sign-off from NYSW, stabilized build, handoff doc drafted. |
| Week of Oct 27 | Rehearsals completed with NYSW, final handoff doc walked through together, Demo Day Oct 28. |

11 · Risks & Dependencies

Risks

- Grading thresholds are not yet finalized; building the scoring engine before thresholds are confirmed risks rework.

- The School Communication Stream export format is still TBD and may not be ready within the build window.

- GST visit photos are uploaded to Google Drive inconsistently (sometimes in batches every ~3 weeks), which may create Snapshot recency gaps.

- NYSW and in-house technologist; Amanda serves as de facto tech lead alongside her existing role, which may limit availability.

Dependencies (blocking items)

- NYSW data-source mapping and admin-access confirmation (Megan/Amanda, with Executive Director and Directors) — blocking the data-inventory deliverable due Week 1.

- NYSW-defined grading thresholds and the two model school profiles — blocking a validated scoring engine by the Week 3 checkpoint.

- Confirmed Grade display format (letter grade vs. traffic-light tier) — needed before UI work begins.

- Data privacy review: GST photos and teacher/admin notes may include images or references to minors and identifiable staff; access and storage approach to be confirmed with NYSW in writing in Week 1.

12 · Stakeholders & Meeting Cadence

| Stakeholder | Role in the Project |
| --- | --- |
| Pedro A. Martins | Builder — Pursuit × Mizuho Nonprofit Builder Program; owns the build, this PRD, and client communication (cc'd to Stef). |
| Megan | NYSW primary point of contact; co-leads data-source mapping, grading refinement, and scheduling. |
| Amanda | De facto NYSW tech lead; co-leads data access, grading refinement, and technical questions. |
| Nishy / Shabiha | NYSW stakeholders supporting scoping and KPI/grading-threshold refinement. |
| Executive Director & Directors | Confirm data sources, admin access, and priorities; final say on scope trade-offs. |
| Stef Barros (Pursuit) | Approves the PRD before build, cc'd on all client communications |

- Weekly contact (minimum) with NYSW — Megan available Fridays once school visits are underway.

13 · Future Roadmap (Post-October)

- Development-team workflow integration (Track 2): Monday.com, Gmail, and Slack — already more than halfway built by NYSW with AI assistance over the summer.

- Automated ingestion of the Accelo School Communication Stream once NYSW defines its export format.

- A fourth grading component — Student Engagement — sourced from teacher surveys.

- Raw data browsing/export views across all source systems for power users.

- Automated capture of external communications (e.g., elected-official correspondence) supporting NYSW's 200+ elected-official reporting workload.

14 · Open Questions

Outstanding items raised during scoping (Aug 26) and follow-up sessions with Megan and Amanda. Answers will directly inform the Week 1–3 build.

| # | Topic | Question / Status |
| --- | --- | --- |
| 1 | Grading thresholds | What separates an "A" school from a "D" school? Open — Megan/Amanda/Shabiha building two model school profiles to anchor the rubric. |
| 2 | Data source scope & access | Which sources (beyond core Accelo assets) are in v1, and does the builder have export/admin access to each? Open — pending consultation with Executive Director and Directors. |
| 3 | Grade display format | Letter grade or traffic-light tier? To be confirmed with NYSW in Week 1. |
| 4 | Communication Stream export | Accelo auto-logs school communications, but the export format is still TBD — treated as Out of Scope until defined. |
| 5 | Visit-frequency normalization | Confirm the exact percentage-of-required-visits formula for schools on weekly vs. monthly cadences. |

15 · MVP Definition

Given a partner school, return its current Grade (with Teacher Engagement, Administration Support, and Classroom Maintenance/GST breakdown), how that Grade has trended over the school year, and a flag if it has dropped below the healthy threshold.

Everything else — the Profile view, the Snapshot, search/filter, and the AI note summary — is built around that single core function. The MVP is a decision-support grading tool powered by NYSW's own operational data. Grading thresholds and a fourth component (Student Engagement) are refinements for v2, contingent on NYSW finalizing its rubric.

Pedro A. Martins · Pursuit × Mizuho Nonprofit Builder Program · September 2026